## Read Me
IAM RFP — Client Discovery Questionnaire
Use after the RFP is read, during clarification / discovery workshops.
Purpose
Turn an RFP into a sized, defensible solution. Every question is tagged with what it informs so the answers feed straight into scope, effort, staffing, licensing, the run model and risk — while surfacing the client's business challenges and pain points in each area.
How to use it
1) Pick the tabs that match the RFP scope. 2) Prioritise questions (mark the must-asks). 3) Capture answers in 'Client response'. 4) Log frustrations in 'Pain point / notes' — these become your win themes. 5) Move every number into the 'Volume Metrics' tab; those drive parametric estimates.
Column legend
ID = reference. Category = the kind of question. Question = what to ask. What it informs = the estimate/solution decision it drives. Client response = their answer. Pain point / notes = challenges, risks, follow-ups.
Reading the categories
Context = framing & drivers. Scope = what's in/out. Volume = the counts that size the work (highlighted amber). Technical / Integration = how things connect. Run = managed-services shape. Commercial = pricing levers. Compliance = regulatory overhead. Pain point = explicit problem to solve (highlighted pink).
Tip — keep the chain intact
Map each answer back to: Requirement -> Scope item -> Activities (WBS) -> Effort driver & assumption -> Effort -> Role split -> FTE -> Cost -> Phase plan. If an answer doesn't move something along that chain, it's nice-to-know, not need-to-know.
Companion files
Pairs with IAM_Mastery_Curriculum.docx (teaching + reference) and IAM_Mastery_Tracker.xlsx (learning tracker).
Tabs in this workbook
Tab | Covers | Primarily drives
Cross-Tower | Org context, drivers, compliance, estate, HR source, environments, commercials | Whole-deal framing, phasing, win themes
Directory Services | Directory estate, consolidation, sync, object volumes | Foundation design, migration effort
Access Management | SSO/MFA/federation, app onboarding by protocol, passwordless | App-onboarding effort (the big driver)
IGA | JML, provisioning, roles, SoD, certifications, connectors | Largest tower effort + run volume
PAM | Vaulting, sessions, JIT, secrets, privileged & service accounts | Account/connector effort, run rotation
EPM | Endpoint local-admin removal, application control, elevation | Endpoint-count sizing, rollout phasing
PKI & CLM | CA estate, certificate volumes, discovery, automation | Build/modernise + automation effort
Identity Proofing | Assurance levels, methods, verification volume, fraud | Per-transaction sizing & licensing
CIAM | External identities, MAU, consent, scale, fraud | Scale/NFR design + MAU licensing
ISPM/ITDR/CIEM | Posture, threat detection, cloud entitlements, NHI | Cross-cutting analytics layer scope
Delivery Functions | Engineering, testing, BA, audit, reporting, PM + run model | Staffing matrix, SLAs, run pricing
Volume Metrics | Consolidated numeric capture across all towers | Parametric estimation inputs

## Cross-Tower
Cross-Tower — discovery questions
Whole-deal framing. Ask these first — they shape phasing, the operating model and your win themes.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
CT-01 | Context | What is driving this programme now — audit finding, breach, M&A, cloud migration, compliance deadline, cost reduction, incumbent exit? | Sets priorities, phasing and win themes; tells you the emotional centre of the bid.
CT-02 | Context | Who are the key stakeholders and decision-makers, and how is success measured for them? | Solution emphasis and governance design.
CT-03 | Scope | Which towers are explicitly in scope, and which are out (CIAM, ISPM, PKI often ambiguous)? | Confirms scope boundary; prevents over/under-scoping.
CT-04 | Scope | Is this SI/Transform, Run/Managed Services, or both? Any transition-in from an incumbent? | Splits the estimate into build vs run; flags transition effort.
CT-05 | Context | What IAM capability exists today (products, versions, in-house vs managed)? | Greenfield vs migration vs enhancement per tower.
CT-06 | Compliance | Which regulations/standards apply — SOX, GDPR, HIPAA, PCI-DSS, ISO 27001, DORA, NIS2, regional? | Adds design, evidence and testing overhead; mandatory controls.
CT-07 | Volume | Total identities to manage: employees, contractors, partners/B2B, service/non-human accounts (counts)? | Core sizing & licensing input across towers.
CT-08 | Volume | Total in-scope applications, and the split by integration protocol (SAML, OIDC, SCIM, LDAP, proprietary/legacy)? | Single biggest effort driver for AM and IGA.
CT-09 | Technical | What are the authoritative source(s) of identity (HR systems) and how clean is the data? | Determines JML automation feasibility and data-cleanup effort.
CT-10 | Volume | How many environments are required (Dev/Test/SIT/UAT/Prod) and is HA/DR needed? | Direct multiplier on build and test effort.
CT-11 | Run | Geographies, languages and time zones for users and for support? | Run shift/location model and localisation effort.
CT-12 | Context | What is the target timeline and are there hard deadline drivers (audit, licence expiry, M&A close)? | Phasing, parallelism and resource ramp.
CT-13 | Integration | Which enterprise systems must we integrate with (ITSM e.g. ServiceNow, SIEM, HR, ticketing)? | Integration effort and dependencies.
CT-14 | Commercial | Expected commercial model — fixed price, T&M, outcome-based, managed service — and any budget envelope? | Pricing approach and risk posture.
CT-15 | Commercial | Who owns software licences — client or supplier — and are licences already procured? | Whether licence cost sits in your price; TCO modelling.
CT-16 | Pain point | What is not working today, and what would 'great' look like in 12 months? | Surfaces pain points and the value story behind every number.
CT-17 | Context | Architecture principles/constraints (Zero Trust, cloud-first, data residency, preferred vendors)? | Design constraints and product fit.

## Directory Services
Directory Services — discovery questions
The identity foundation. Sizing here is about directories, objects and the apps that bind to them.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
DIR-01 | Scope | What directories exist today — AD DS, Entra ID, LDAP, Oracle, others — and which are in scope? | Greenfield vs consolidation vs sync scope.
DIR-02 | Volume | How many domains, forests or directory instances must be integrated or consolidated? | Consolidation effort and topology design.
DIR-03 | Volume | How many identity objects (users, groups, devices) per directory? | Migration/sync sizing and licensing.
DIR-04 | Technical | What is the desired source of truth, and which attributes must flow where (incl. write-back)? | Synchronisation design and connector effort.
DIR-05 | Pain point | What is the health of the current directory — stale objects, schema sprawl, GPO complexity, duplicate identities? | Remediation effort; common hidden cost.
DIR-06 | Scope | Are hybrid join, device identity or workstation authentication in scope? | Adds device-identity workstreams.
DIR-07 | Scope | Is this an M&A / multi-org scenario needing a virtual directory or identity data fabric? | Radiant-Logic-style consolidation effort.
DIR-08 | Volume | How many security/distribution groups, and is group lifecycle management in scope? | Governance and migration volume.
DIR-09 | Volume | How many applications authenticate directly to the directory (LDAP/Kerberos binds)? | Migration risk and re-pointing effort.
DIR-10 | Technical | What are the HA/DR, replication and site topology requirements? | Environment and resilience design.
DIR-11 | Pain point | How are directory objects managed today (manual, scripted, delegated) and what breaks? | Automation opportunity and run baseline.

## Access Management
Access Management — discovery questions
SSO/MFA/federation. Application onboarding by protocol is the dominant effort driver here.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
AM-01 | Scope | What SSO, MFA and federation products are in place today, and what is the target? | Greenfield vs migration vs coexistence.
AM-02 | Volume | How many applications need SSO, broken down by protocol (SAML, OIDC/OAuth, WS-Fed, header-based, password-vaulting)? | Primary parametric driver; standards = cheap, legacy = expensive.
AM-03 | Volume | How many of these are already integrated vs net-new onboarding? | Separates migration from new build.
AM-04 | Scope | Current and target MFA methods — and is passwordless / FIDO2 / passkeys in scope? | Effort and rollout complexity.
AM-05 | Volume | How many users must be enrolled in MFA, and over what rollout window? | Adoption/rollout effort and comms.
AM-06 | Volume | How many conditional / risk-based access policies are required, and how complex? | Policy configuration and testing effort.
AM-07 | Volume | How many B2B/external federation partners or trusts are in scope? | Federation setup volume.
AM-08 | Technical | Which legacy authentication patterns must be modernised (Kerberos, basic auth, header-based)? | High-effort, high-risk items; proxy/bridge needs.
AM-09 | Scope | Are self-service password reset and self-service MFA management in scope? | L1 volume-reduction lever and benefit case.
AM-10 | Volume | What is the peak authentication load (logins/day, concurrent sessions)? | Non-functional sizing and infrastructure.
AM-11 | Integration | What is the IdP topology and directory dependency (single IdP, hub-and-spoke, multi-IdP)? | Architecture and integration effort.
AM-12 | Pain point | Where is the friction today — password resets, onboarding backlog, login experience, outages? | Pain points and quantified benefit.

## IGA
IGA — discovery questions
Usually the largest tower. Connectors, use cases and certification scale drive the number.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
IGA-01 | Scope | What is the current IGA state — manual, scripted, or a product (which/version)? | Greenfield vs migration; biggest transformation opportunity.
IGA-02 | Volume | How many identities will be under governance, by type (employee, contractor, partner, service)? | Licensing and run sizing.
IGA-03 | Volume | How many applications need full provisioning vs governance-only (read) integration? | Connector build effort — the core IGA driver.
IGA-04 | Volume | For the provisioning apps, how many use out-of-the-box connectors vs custom/legacy? | Custom connectors are the expensive line item.
IGA-05 | Volume | How many roles exist today and how many are targeted? Is role mining/redesign needed? | Role-engineering effort; AI role-mining opportunity.
IGA-06 | Volume | Access request catalogue size and approval workflow complexity (number of levels, conditional routing)? | Workflow build and test effort.
IGA-07 | Volume | Certification campaigns: which populations, what frequency, how many reviewers, lines per campaign? | Large recurring run effort; automation ROI.
IGA-08 | Volume | Segregation-of-Duties: how many SoD rules, what source, and what is the remediation process? | Ruleset build and ongoing run effort.
IGA-09 | Volume | JML volumes: joiners, movers and leavers per month / per year? | Run FTE sizing and automation business case.
IGA-10 | Technical | How reliable is mover/leaver detection from the HR feed (terminations, transfers)? | Automation feasibility; audit-risk reduction.
IGA-11 | Compliance | What audit and attestation evidence must IGA produce (who-has-access, campaign sign-off)? | Reporting build and run evidence effort.
IGA-12 | Scope | Is AI-assisted governance in scope (outlier/peer-group analytics, access recommendations)? | Differentiator and certification volume reduction.
IGA-13 | Pain point | Biggest governance pain — leaver revocation gaps, audit findings, certification fatigue, slow provisioning? | Pain points and benefit framing.

## PAM
PAM — discovery questions
Privileged and non-human accounts. Discovery of unknown accounts is a frequent hidden cost.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
PAM-01 | Scope | Current PAM state and product (if any); what is the target capability set? | Greenfield vs migration vs extend.
PAM-02 | Volume | How many privileged accounts must be vaulted — human admins and service/non-human accounts? | Core licensing and onboarding driver.
PAM-03 | Volume | How many target systems by type (Windows, Unix/Linux, databases, network devices, cloud, SaaS)? | Connector/platform onboarding effort.
PAM-04 | Volume | Are service/non-human accounts already inventoried, or is discovery required? Estimated count? | Discovery effort; usually a major hidden scope item.
PAM-05 | Scope | Session management and recording scope — which assets, and is live monitoring required? | Session-tier effort and storage sizing.
PAM-06 | Scope | Is just-in-time access / Zero Standing Privilege in scope, or vaulting only? | Significant design-complexity step-up.
PAM-07 | Volume | Secrets/credential management for applications, CI/CD and DevOps — how many secrets/consumers? | Secrets-management workstream sizing.
PAM-08 | Scope | Cloud privileged access (AWS/Azure/GCP) and any CIEM overlap? | Cross-tower scope with ISPM/CIEM.
PAM-09 | Run | Credential rotation policies and frequency by account type? | Recurring run effort and risk posture.
PAM-10 | Technical | Break-glass / emergency access requirements and approval flow? | Critical design and audit item.
PAM-11 | Integration | Integration with SIEM/ITDR for privileged-session analytics? | Integration effort; monitoring value.
PAM-12 | Pain point | Current pain — shared admin passwords, no rotation, standing privilege, audit gaps? | Pain points and compelling risk story.

## EPM
EPM — discovery questions
The endpoint arm of privileged access — endpoint count and OS mix size it, and rollout almost always runs in audit mode before enforce.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
EPM-01 | Scope | Do endpoint users currently hold standing local administrator rights, and is removing them the goal? | Baseline risk and the core transformation; sets the before/after story.
EPM-02 | Volume | How many endpoints are in scope, broken down by OS (Windows / macOS / Linux)? | Core sizing and per-endpoint licensing; multi-OS raises effort.
EPM-03 | Scope | Which capabilities are wanted — local-admin removal, application control / allow-listing, on-demand elevation, or all? | Scope boundary and product fit.
EPM-04 | Volume | Roughly how many distinct applications will need elevation or allow-list rules? | Policy authoring effort — a primary build driver.
EPM-05 | Volume | How many user personas / groups have different privilege needs (developers, engineers, standard staff)? | Policy-model complexity and rule grouping.
EPM-06 | Technical | What endpoint-management tooling is in place (Intune, SCCM, Jamf, Tanium) for agent deployment? | Deployment path and integration effort.
EPM-07 | Run | Will rollout run in audit / monitor mode first to learn real usage, and over what window before enforcing? | Phasing, timeline and business-disruption risk — price it explicitly.
EPM-08 | Scope | Is macOS and/or Linux coverage required, or Windows only? | Effort and product selection (Microsoft Intune EPM is Windows-only today).
EPM-09 | Integration | Integration with directory groups (AD/Entra) and SIEM/EDR for elevation logging? | Integration effort and SOC value.
EPM-10 | Compliance | What is the driver — cyber-insurance requirement, CIS / Essential Eight, audit finding, ransomware reduction? | Urgency and win theme; mandated controls.
EPM-11 | Run | Who handles elevation requests, exceptions and new-app rules in BAU, and what volume is expected? | Run FTE sizing and operating model.
EPM-12 | Commercial | Standalone EPM, or a module of an existing PAM suite already in the estate? | Licensing basis and integration; convergence opportunity.
EPM-13 | Pain point | Current pain — malware/ransomware incidents, local-admin sprawl, helpdesk admin-rights tickets, audit findings? | Pain points and quantified benefit.

## PKI & CLM
PKI & CLM — discovery questions
Certificate volumes and the shift to short-lived certs make automation the central theme.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
PKI-01 | Scope | Current PKI estate — internal CA (AD CS), public CA vendors, and any CLM tooling? | Build vs modernise scope.
PKI-02 | Volume | How many certificates are in the estate (active/issued), by type (TLS, client, code-signing, device)? | Core sizing and licensing driver.
PKI-03 | Volume | How many CAs and what hierarchy (root, issuing, sub-CAs)? | CA design and migration effort.
PKI-04 | Pain point | Has a certificate discovery been done — what is known vs unknown / unmanaged? | Discovery effort; expired-cert outage risk.
PKI-05 | Volume | How many endpoints, devices and applications consume certificates? | Automation integration scope.
PKI-06 | Technical | Current automation maturity — manual/spreadsheet, ACME, or API-driven renewal? | Largest effort and biggest opportunity area.
PKI-07 | Scope | Readiness for shorter certificate lifetimes (CA/Browser Forum reductions) — is automated renewal mandated? | Drives the automation business case.
PKI-08 | Compliance | HSM, key-ceremony and compliance (e.g. FIPS) requirements? | Specialist effort and infrastructure.
PKI-09 | Scope | Crypto-agility / post-quantum readiness ambition? | Forward-looking scope and design.
PKI-10 | Volume | How many certificate renewals per year, and what is the outage history from expiries? | Run effort and quantified pain.
PKI-11 | Integration | Which platforms need auto-renewal integration (load balancers, web servers, network kit, Kubernetes, DevOps)? | Integration volume for CLM.
PKI-12 | Pain point | Biggest current pain — outages from expired certs, manual tracking, unknown certs, audit gaps? | Pain points and benefit story.

## Identity Proofing
Identity Proofing — discovery questions
Assurance level and verification volume drive both effort and per-transaction licensing.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
IDP-01 | Scope | Is proofing for workforce onboarding, customer/CIAM onboarding, or both? | Scope and which platform pattern applies.
IDP-02 | Compliance | What assurance levels are required (NIST IAL/AAL, eIDAS) or KYC/AML obligations? | Mandatory controls and design rigour.
IDP-03 | Scope | Which verification methods — document, biometric/liveness, database/knowledge, attended review? | Method scope and orchestration effort.
IDP-04 | Volume | Expected verification volume per month and at peak? | Per-transaction licensing and NFR sizing.
IDP-05 | Scope | What fraud, deepfake and injection-attack controls are required? | Adds anti-fraud scope (NIST 800-63 Rev 4).
IDP-06 | Volume | Which geographies and document types must be supported? | Coverage complexity and vendor selection.
IDP-07 | Integration | How does proofing fit the onboarding journey — orchestration, fallbacks, manual review? | Integration and process design effort.
IDP-08 | Scope | Is reusable identity / verifiable credentials in scope? | Forward-looking scope.
IDP-09 | Pain point | Current pain — onboarding drop-off, fraud losses, manual-review backlog? | Pain points and quantified benefit.

## CIAM
CIAM — discovery questions
External identity at scale. Pin down MAU and peak load — the cost model swings on traffic, not headcount.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
CIAM-01 | Scope | Is this B2C, B2B or B2B2C, and what is the expected external identity population? | Pattern, scale and licensing basis.
CIAM-02 | Volume | Expected monthly active users (MAU), peak concurrent users and authentications per period? | MAU/transaction licensing and NFR sizing.
CIAM-03 | Scope | Required registration/login methods — social login, passwordless, federation, SSO across properties? | Feature scope and integration effort.
CIAM-04 | Scope | Is progressive profiling and preference/consent management required? | Privacy and journey-build scope.
CIAM-05 | Compliance | Which privacy regimes apply (GDPR, CCPA) and what consent capabilities are needed? | Compliance and consent-management effort.
CIAM-06 | Scope | Bot defence, fraud and account-takeover protection requirements? | Anti-fraud scope and tuning.
CIAM-07 | Volume | Existing customer identity stores to migrate — how many, and what data quality? | Migration effort and de-duplication.
CIAM-08 | Volume | How many brands, journeys or tenant configurations must be supported? | Customisation and build volume.
CIAM-09 | Technical | Availability/SLA and regional/residency requirements? | Architecture, scale and resilience design.
CIAM-10 | Integration | Integration with marketing/CRM/CDP/analytics platforms? | Integration scope.
CIAM-11 | Pain point | Current pain — registration friction, breach exposure, fragmented customer identities? | Pain points and value story.

## ISPM ITDR CIEM
ISPM ITDR CIEM — discovery questions
Posture and threat layers over the towers. Usually reads from the IGA/PAM/directory you are already building.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
ISPM-01 | Scope | What is the primary goal — posture visibility (ISPM), threat detection/response (ITDR), cloud entitlements (CIEM), or all? | Scope boundary across the trio.
ISPM-02 | Volume | Which directories, IdPs and identity stores must be assessed for posture? | Assessment coverage and connector effort.
ISPM-03 | Pain point | What issues are suspected — stale/orphaned accounts, shadow admins, MFA gaps, excess privilege, risky NHIs? | Surfaces the problem set and value.
ISPM-04 | Volume | Which cloud platforms (AWS/Azure/GCP) and how many accounts/subscriptions for CIEM? | CIEM sizing and integration.
ISPM-05 | Volume | Estimated number of non-human identities (service accounts, workloads, agents) in scope? | Fast-growing scope area; sizing.
ISPM-06 | Integration | Which SIEM/SOC/EDR platforms must ITDR integrate with, and what response is expected? | Integration effort and run model.
ISPM-07 | Scope | Real-time detection and automated response expectations, or reporting/posture only? | Effort and operating-model step-up.
ISPM-08 | Scope | Risk-scoring, dashboards and reporting requirements for posture? | Reporting build effort.
ISPM-09 | Technical | Any existing tooling (Microsoft Entra, Silverfort, CrowdStrike, SailPoint/Saviynt ISPM, Veza)? | Build-on vs greenfield.
ISPM-10 | Pain point | Any prior identity-attack history or audit findings on identity visibility? | Pain points and urgency.

## Delivery Functions
Delivery Functions — discovery questions
The 'how' — these answers shape the staffing matrix (bands x functions), SLAs and run pricing, not tower scope.
ID | Category | Question | What it informs (estimate / solution driver) | Client response | Pain point / notes
DF-01 | Scope | Is the engagement SI/Transform, Run/Managed Services, or both — and is there a transition-in from an incumbent? | Splits build vs run; transition effort and risk.
DF-02 | Commercial | Delivery model — onsite/nearshore/offshore mix, permitted locations, support data-residency rules? | Rate card and therefore price.
DF-03 | Technical | Which environments and access will the delivery team get, and how is access granted? | Mobilisation timeline and risk.
DF-04 | Run | Ways of working — Agile/Waterfall/SAFe — and whose tooling (Jira/Azure DevOps/ServiceNow)? | Process overhead and ceremonies.
DF-05 | Run | Expected governance and reporting cadence (steering, status, RAID)? | Project-management effort (PMO).
DF-06 | Run | Service hours required — 8x5, 24x7, follow-the-sun? | Major run headcount and cost driver.
DF-07 | Run | SLA targets by priority (response and resolution) and any penalty/credit regime? | Staffing intensity and on-call cost/risk.
DF-08 | Volume | Expected ticket volumes by tier (L1/L2/L3) per month? | Run FTE sizing — the core run driver.
DF-09 | Volume | Split of incidents vs service requests vs onboarding requests? | Skill mix and automation targeting.
DF-10 | Volume | Application/account onboarding cadence expected in Run (per month)? | Recurring run capacity (parametric).
DF-11 | Volume | Certification campaign frequency and size during Run? | Recurring governance run effort.
DF-12 | Run | Testing — client UAT involvement, test environments, and automation expectations? | Test-function effort and timeline.
DF-13 | Run | Business Analysis — who provides requirements and SMEs client-side, and what is their availability? | Discovery risk and BA loading.
DF-14 | Compliance | Audit & compliance — audit calendar, evidence expectations, internal/external auditors involved? | Audit-support run effort.
DF-15 | Run | Reporting — required dashboards/KPIs, tooling (e.g. Power BI), and frequency? | Reporting-function effort.
DF-16 | Commercial | Automation / continuous-improvement targets — expected year-on-year volume or cost reduction? | Commercial lever and differentiator.
DF-17 | Commercial | Which tools are client-provided vs supplier-provided (ITSM, monitoring, IAM platforms)? | Cost ownership and integration.
DF-18 | Pain point | Current run pain — SLA breaches, backlog, attrition, knowledge gaps, incumbent issues? | Pain points and transition risk.

## Volume Metrics
Volume Metrics — consolidated estimation inputs
The numbers that feed parametric sizing. Capture 'Current' and a 'Target / Year 2' where growth matters.
Tower / area | Metric | Unit | Why it matters (drives) | Current | Target / Yr2
Workforce | Total identities | count | Cross-tower sizing & licensing
Workforce | Employees / contractors / partners | count | Identity-type licensing nuances
Workforce | Service / non-human accounts | count | PAM + governance scope
Applications | Total in-scope applications | count | Top AM/IGA effort driver
Applications | Apps by protocol: SAML / OIDC / SCIM / LDAP / legacy | count each | Standards cheap, custom expensive
Environments | Environment count (non-prod tiers + prod) | count | Build/test effort multiplier
Environments | HA/DR required | Y/N | Resilience design & infra
JML | Joiners / Movers / Leavers per year | count/yr | Run sizing & automation ROI
IGA | Identities under governance | count | Licensing & run volume
IGA | Connectors: out-of-box / custom | count each | Connector build effort
IGA | Roles: current / target | count | Role-engineering effort
IGA | Certifiable lines per campaign / frequency | count, per yr | Recurring certification effort
IGA | SoD rules | count | Ruleset build & remediation
Access | Users for MFA enrolment | count | Rollout effort
Access | Conditional-access policies | count | Policy config & test effort
Access | B2B federation partners | count | Federation setup volume
Access | Peak logins per day / concurrent | count | Non-functional sizing
PAM | Privileged accounts (human) | count | Onboarding & licensing
PAM | Service / non-human accounts | count | Discovery & onboarding
EPM | Endpoints in scope (total) | count | Core EPM sizing & licensing
EPM | Endpoints by OS: Windows / macOS / Linux | count each | Multi-OS raises effort & product choice
EPM | Applications needing elevation/allow-list rules | count | Policy authoring effort
EPM | User personas / privilege groups | count | Policy-model complexity
EPM | Elevation requests per month (run) | count/mo | Run FTE sizing
PAM | Target systems by type | count each | Platform connector effort
PAM | Sessions recorded per day / secrets managed | count | Session tier & storage; secrets scope
PKI | Active certificates | count | Core CLM sizing
PKI | CAs in hierarchy | count | CA design effort
PKI | Renewals per year | count/yr | Run effort & automation case
PKI | Auto-renewal endpoints / unknown certs found | count | Integration volume & discovery
Proofing | Verifications per month / peak per day | count | Per-transaction licensing & NFR
CIAM | External identities / MAU | count | Scale & MAU licensing
CIAM | Peak concurrent / auths per period | count | NFR & licensing
CIAM | Brands / journeys | count | Customisation effort
ISPM/CIEM | Directories & IdPs assessed | count | Assessment coverage
ISPM/CIEM | Cloud accounts / subscriptions | count | CIEM sizing
ISPM/CIEM | Non-human identities in scope | count | Posture scope
Run | Ticket volume per month: L1 / L2 / L3 | count/mo | Run FTE sizing
Run | Onboarding requests per month | count/mo | Recurring run capacity
Run | Service hours (8x5 / 24x7 / FTS) | model | Headcount & cost driver